## Board
STORIES | NOT DONE | IN PROGRESS... | DONE | DROPPED
STORY # 01:
File Handling
STORY # 02:
User Account Interface
STORY # 02 - TASK # 01: Create methods to display reservations
STORY # 01 - TASK # 01: Create methods to access the Database
STORY # 03:
Admin Account Interface
STORY # 04:
Database: Login, Registration, and Users
STORY # 02 - TASK # 02: Connect data for Scheduling
STORY # 02 - TASK # 03: Connect data for user credentials
STORY # 04 - TASK # 01: Populate the Database
STORY # 02 - TASK # 03: Fix methods for data access
STORY # 02 - TASK # 02: Create method to restrict available time start and time end
STORY # 02 - TASK # 03: Create methods save reservation to the database
STORY # 02 - TASK # 04: Fix methods for user interface
STORY # 03 - TASK # 01: Create methods to display reservations
STORY # 03 - TASK # 02: Create method to restrict available time start and time end
STORY # 03 - TASK # 03: Create methods save reservation to the database
STORY # 03- TASK # 04: Fix methods for admin interface
STORY # 03- TASK # 05: Create methods to remove and edit account
STORY # 03- TASK # 06: Fix form of interface

## Availability Estimate
Availability Estimate
weekday | M | T | W | R | F | S | S
month | October
Resource | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14
Resource | Sprint #3 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Calites, John Vincent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fradejas, Dayne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reyes, Jean Tristan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Until the end of the Sprint | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Sprint | 0

## Actual Spent Time
Actual Availability
weekday | M | T | W | R | F | S | S
month | September
Resource | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14
Resource | Sprint #2 | [6 empty] | Total per Resource
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Calites, John Vincent | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fradejas, Dayne | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reyes, Jean Tristan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Day | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Until the end of the Sprint | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total per Sprint | 0

## Product BackLog
Product BackLog
Stories
State | Name | Description | Points
Done! | File Handling | Created Login class | 21
Done! | User Account Interface | Created class for file handling login | 21
Done! | Admin Account Interface | Created Signup class | 34
Done! | Database | Created class for file handling sign up | 13
Note on B2: A prioritized list of high-level requirements.
Note on B4: INVEST in stories: - Independent - Negotiable - Valuable - Estimable - Small - Testable

## 3rd Sprint
|  |  |  | 24 | M | T | W | R | F | S | S
Story | Task | Category | Who | 5 | Time to finish task (person/hour)
|  |  |  | Estimate | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14
Ideal Execution |  |  |  | 54 | 43.2 | 32.4 | 21.6 | 10.8 | 3.5527e-15 | 0 | 0
Total per Day |  |  |  | 54 | 24 | 19 | 9 | 11 | 1 | 4 | 9
Data Access | Create methods to access the database | Code | Dayne | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Create methods to get user credentials | Code | Dayne | 4 | 4 | 1 | 0 | 0 | 0 | 0
| Create methods to get reservation schedule | Code | Dayne | 4 | 2 | 3 | 0 | 0 | 0 | 0 | 0
| Code Fixes | Bug-Fix | Dayne | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
[14 empty] | M | T | W | R | F | S | S
User Interface | Create methods to display reservations | Code | Jean Tristan | 6 | 3 | 1 | 3 | 4 | 0 | 0 | 0 |  | Estimate | 2018-10-08 | 2018-10-09 | 2018-10-10 | 2018-10-11 | 2018-10-12 | 2018-10-13 | 2018-10-14
| Create methods to restrict the time start and time end | Code | John Vincent | 6 | 3 | 2 | 0 | 0 | 0 | 0 | 0
| Create methods to save reservation on the database | Code | John Vincent | 3 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | Ideal | 54 | 43.2 | 32.4 | 21.6 | 10.8 | 3.5527e-15 | 0 | 0
| Code Fixes | Bug-Fix | John Vincent and Jean Tristan | 3 | 0 | 0 | 0 | 2 | 1 | 1 | 5 | Real | 54 | 24 | 19 | 9 | 11 | 1 | 4 | 9
Admin Interface | Create methods to display reservations | Code | Jean Tristan | 6 | 2 | 2 | 1 | 2 | 0 | 0 | 0 | Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create methods to restrict the time start and time end | Code | John Vincent | 6 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | Code | 45 | 21 | 16 | 9 | 9 | 0 | 0 | 0
| Create methods to save reservation on the database | Code | John Vincent | 3 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Code Fixes | Bug-Fix | Dayne and John Vincent | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Bug-Fix | 9 | 3 | 3 | 0 | 2 | 1 | 4 | 9
Database | Populate the Database | Code | All members | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Note on C3: SMART Tasks: - Specific - Measurable - Achievable - Relevant - Time-Boxed

## Check
Fibonnaci | Status | Category | Person
0 | Dropped | Design | Dayne
0.5 | Done! | Code | John Vincent
1 | Blocked | Testing | Jean Tristan
2 | Ongoing | Bug-Fix | Dayne and John Vincent
3 | Planned |  | Dayne and Jean Tristan
5 |  |  | John Vincent and Jean Tristan
8 |  |  | All members
13
21
34
55
89
∞